## Page Inventory
Rebekah's Health & Nutrition - Phase One Page Inventory
Non-ecommerce scope. Rows 17-20 are proposed affiliate/referral landing pages pending program verification.
# | Page | Proposed URL | Family | Design Status | Build Status | Priority | Notes / Decisions | SEO & Content Focus | Next Step
1 | Home | / | Core | Design complete | Implement | High | Combined Homepage v1.21 is the production reference. | Homepage title/meta, local wellness intent, four-store trust signals, internal links, Organization/LocalBusiness structure. | Implement in WordPress; optimize 56 MB hero video; connect social feeds and forms.
2 | Our Story / Meet Rebekah | /our-story/ | Core | Design complete | Implement | High | Our Story v1.1.6 is approved. Merge Meet the Owner into this canonical page. | Founder/entity signals, Michigan wellness-store history, credentials, E-E-A-T, factual milestones, internal links. | Implement in WordPress; redirect /meet-the-owner/; validate researched facts with Rebekah.
3 | Locations | /locations/ | Locations | Needs design | Not started | High | Hub for all four stores. | Michigan location intent, clear NAP information, store comparison, links to each location. | Create concise hub using the approved design system.
4 | Lapeer Location | /locations/lapeer/ | Locations | Needs design | Not started | High | Confirmed individual store page. | Unique local copy, address/phone/hours/map, services, photos, events, reviews, LocalBusiness schema. | Research and build in its own task using the shared location template.
5 | Grand Blanc Location | /locations/grand-blanc/ | Locations | Needs design | Not started | High | Confirmed individual store page. | Unique local copy, address/phone/hours/map, services, photos, events, reviews, LocalBusiness schema. | Research and build after the location template is approved.
6 | Clarkston Location | /locations/clarkston/ | Locations | Needs design | Not started | High | Confirmed individual store page. | Unique local copy, address/phone/hours/map, services, photos, events, reviews, LocalBusiness schema. | Research and build after the location template is approved.
7 | Lake Orion Location | /locations/lake-orion/ | Locations | Needs design | Not started | High | Confirmed individual store page. | Unique local copy, address/phone/hours/map, services, photos, events, reviews, LocalBusiness schema. | Research and build after the location template is approved.
8 | Classes & Events | /events/ | Content archive | Needs design | Not started | High | Client priority; existing event content must be preserved. | Local class/event intent, crawlable event copy, Event schema where appropriate, location and topic linking. | Confirm registration scope; design archive and event-detail template together.
9 | Wellness Source Blog | /blog/ | Content archive | Minimal design | Not started | Medium | Very light design: intro, useful filters/search, and post grid. | Archive title/meta, topical organization, internal linking, author/reviewer signals; SEO value primarily comes from posts. | Build after global styles; avoid overdesigning the archive.
10 | In-Store Products | /in-store-products/ | Products | Needs design | Not started | High | Non-transactional discovery page; no ecommerce. | Product-category discovery, featured brands, Signature Line, store availability caveat, visit/call conversion paths. | Define categories and brands; build a rich informational page without prices, cart, or checkout.
11 | Practitioners | /practitioners/ | Directory | Needs design | Not started | Medium | Existing structured directory with 28 records. | Practitioner specialties, locations, credentials, unique bios, internal links; avoid thin/duplicate profiles. | Decide whether individual profiles stay public; build archive and detail template together.
12 | Contact Us | /contact-us/ | Utility | Light redesign | Not started | High | Reuse and retest the existing contact form. | Clear store/contact intent, NAP consistency, spam/consent controls, conversion tracking. | Build after location data is finalized; verify notifications and delivery.
13 | Privacy Policy | /privacy-policy/ | Legal | Reuse / quick revision | Not started | Medium | Current policy will be used and fitted to the new design. | Clear crawlable policy, accurate services/cookies/forms/vendors, updated effective date. | Apply legal-page template; revise only where site functionality requires it; seek legal review for material changes.
14 | Refund & Returns Policy | /refund_returns/ | Legal | Reuse current | Not started | Medium | Current policy will remain available even while onsite ecommerce is deferred. | Accurate scope and contact process; prevent conflicts with external partner purchase policies. | Apply legal-page template and confirm policy still matches actual operations.
15 | Terms & Conditions | /terms-conditions/ | Legal | New template/content | Not started | Medium | New page required. | Website use, intellectual property, external links, purchases/referrals, limitations, governing terms. | Draft starter copy based on actual site functionality; obtain qualified legal review before launch.
16 | Disclaimer | /disclaimer/ | Legal | New template/content | Not started | High | New wellness/educational disclaimer required. | Educational-not-medical-advice language, claims boundaries, professional consultation, affiliate disclosure alignment. | Draft with claims-safe language; obtain qualified legal review before launch.
17 | Shop Fullscript | /shop-fullscript/ | Affiliate | Proposed landing page | Verify program | Medium | External transaction; no onsite cart. | Useful original explanation, appropriate audience, ordering process, affiliate disclosure, external-link labeling. | Confirm exact URL/account/disclosures, then build a concise affiliate landing page.
18 | Shop Designs for Health | /shop-designs-for-health/ | Affiliate | Proposed landing page | Verify program | Medium | External transaction; no onsite cart. | Useful original explanation, ordering process, product/medical claim controls, affiliate disclosure. | Confirm exact URL/account/disclosures, then build from the affiliate-page template.
19 | Shop LifeWave | /shop-lifewave/ | Affiliate | Proposed landing page | Verify program | Medium | Currently promoted through the Practitioners menu. | Original explanatory content, careful wellness claims, ordering relationship, affiliate disclosure. | Confirm exact URL/account/disclosures, then build from the affiliate-page template.
20 | Peptides & Injectables | /peptides-injectables/ | Referral / affiliate | Proposed landing page | Verify program | High | Current navigation and approved homepage reference injections. | Especially careful medical/eligibility language, provider relationship, disclosures, external/referral CTA; avoid unsupported claims. | Clarify whether this is affiliate, referral, direct contact, or clinical service before drafting.

## Templates & Global
Reusable Templates and Global Work
Type | Component | Applies To | Notes
Template | Blog post | 21 existing posts | Build once; preserve URL, author, date, category, image and SEO data; strengthen expertise, sourcing and internal links.
Template | Event detail | Existing and future events | Build once with location/date/organizer structure and Event schema where appropriate.
Template | Practitioner profile | 28 practitioner records | Build once if profiles remain public; require meaningful unique bios and credentials.
Template | Location detail | Four store pages | Approve Lapeer first as the master, then adapt with genuinely unique store content.
Template | Affiliate landing page | Four proposed partner/referral pages | Reusable structure, but every page needs original partner-specific copy and disclosure.
Template | Legal page | Privacy, Returns, Terms, Disclaimer | Shared clean typography and navigation; content differs per policy.
Global | Header and navigation | Sitewide | Use the final Combined Homepage v1.21 direction and approved page labels.
Global | Footer | Sitewide | Include locations, policies, contact details, social links and legal navigation.
Global | Newsletter and text signup | Sitewide / selected pages | Preferred-store field is required; confirm integrations, consent, routing and delivery.
Global | Instagram and TikTok feeds | Homepage / selected pages | Requires plugin setup and account authorization; use crawlable surrounding copy.
Global | Search and 404 | Sitewide | Create useful search/empty states and a branded 404 with recovery links.
Global | SEO system | Sitewide | Titles/metas, canonicals, redirects, schema, breadcrumbs, XML sitemaps, image SEO, internal linking and QA.

## Recommended Workflow
Recommended Codex Task Workflow
Use one task per substantive page or page family. Begin every task by referencing Homepage v1.21, Our Story v1.1.6, the brand kit, this Sheet, and the approved image-source rules.
Order | Stage | Task Structure | What Happens
1 | Lock shared standards | One setup task | Create the reusable design system, SEO checklist, copy/claims rules, schema plan and internal-link map from Homepage v1.21 and Our Story v1.1.6.
2 | Implement approved pages | One task per page | Home, then Our Story. These establish the WordPress global styles and reusable sections.
3 | Build page families | One task per family | Locations hub + Lapeer master template; Events archive + detail; Practitioners archive + detail; affiliate template + first verified partner.
4 | Adapt family pages | One task per page | Grand Blanc, Clarkston and Lake Orion each get their own research, unique copy and SEO—not search-and-replace duplicates.
5 | Build supporting pages | One task per substantive page | In-Store Products, Contact, affiliate/referral pages and legal content. Blog archive can share a small implementation task.
6 | Perform integrated SEO QA | One final sitewide task | Check crawlability, metadata, canonicals, redirects, schema, internal links, mobile, accessibility, forms, analytics and performance.